CHULALONGKORN UNIVERSITY · FACULTY OF ENGINEERING

Seating & Event Availability Tracking System (SEATS)
for La Loy Restaurant

Milestone 2 Final Deliverable:
Project Management Plan — Scope, WBS, Effort, Resources, Cost Baseline, Gantt Chart and Critical Path

Course: 2110722 Software Project Management
Submitted to: Assoc. Prof. Twittie Senivongse

By: SE69 Group 1 (regular program)
• Boonnisa Tangjitpermkwamdee   Student ID 6970156821
• Sirapatr Chalermwattanatrai   Student ID 6970292421
• Chawanakorn Sanannam          Student ID 6970064721
• Watayut Aiamanan              Student ID 6970267821

Version 1.0 · October 2026
Department of Computer Engineering, Faculty of Engineering, Chulalongkorn University
Semester 1, Academic Year 2569

Table of Contents

1. Project Scope Statement	3

1.1. Project summary	3

1.2. Product characteristics and requirements	3

1.3. Project deliverables	3

1.4. Exclusions	4

1.5. Success criteria	4

2. Work Breakdown Structure (WBS) and Tasks	4

2.1. WBS dictionary (summary)	6

2.2. WBS dictionary (worked examples)	6

3. Effort Estimation	6

3.1. Effort by role	7

4. Human and Physical Resource Assignment and Rates	7

5. Cost Estimate	8

5.1. Cost-control rules	8

6. Schedule, Gantt Chart and Critical Path	8

6.1. Iteration schedule	9

6.2. Gantt chart view	9

6.3. Critical path (dependency-based planning estimate)	10

6.4. Milestone control points	10

7. Conclusion	11

# 1. Project Scope Statement

## 1.1. Project summary

The Seating & Event Availability Tracking System (SEATS) is a LINE-integrated web application for reserving tables at La Loy Restaurant's live-music concerts. Customers use a LIFF web app to browse concerts, view a live table map, select a table, hold it for 15 minutes, pay the full table fee through a payment gateway, and receive a QR e-ticket. Restaurant staff use a shared back office to monitor bookings, handle exceptions and scan QR codes at check-in. The system uses one central record to reduce double bookings and payment-related disputes. After the initial implementation, the system is piloted at La Loy and productized as a multi-tenant subscription service for other live-music restaurants.

The project runs from 3 August 2026 to 28 July 2028 (24 calendar months / 2 project years): Year 0 builds and deploys Release 1.0 Core (2 April 2027) and Release 2.0 Growth (30 July 2027); Year 1 runs the live pilot and delivers Release 2.1 SaaS productization (11 February 2028), closing with the expansion decision on 28 July 2028.

## 1.2. Product characteristics and requirements

The functional requirements use the R1-R7 identifiers of the requirements-engineering report; the quality and compatibility characteristics are taken from the project-management report.

| Requirement / area | In-scope characteristics / requirements |
| --- | --- |
| R1 (LINE self-service channel) | Mobile-first LIFF web app accessed via the LINE Rich Menu to browse concert rounds, view a live table map, select packages/tables and obtain QR e-tickets. |
| R2 (Real-time hold and inventory control) | One central database with an automatic 15-minute table lock (first lock wins) that prevents double bookings; table status is maintained in real time. |
| R3 (Automated payment gateway) | Payment-gateway checkout (PromptPay QR and cards) with automatic webhook confirmation of the full table fee. |
| R4 (Shared back-office console) | Real-time web dashboard for Manager, Owner and Front Staff to manage rounds, table layouts, pricing packages, manual overrides and audit trails. |
| R5 (Door check-in and validation) | Mobile QR e-ticket scanning at the venue door, target check-in time of no more than 15 seconds per table, with instant name/phone lookup. |
| R6 (Growth features, Release 2.0) | Automated LINE push reminders, 30-minute grace extension, waitlist queuing, official booking transfer and operational reports. |
| R7 (Multi-tenant architecture, Release 2.1) | Multi-tenant data isolation, self-service venue onboarding, subscription plans and limits (Free, Standard, Premium), automated tier enforcement and administrative billing. |
| Quality and operations | Target response time of no more than 2 seconds for customer/front-staff transactions; check-in within 15 seconds per table; support at least 5 transactions per second at booking-open; daily backup with Excel export; recovery within 2 hours during opening hours. |
| Compatibility and compliance | Current LINE in-app browser and the last two versions of Chrome, Safari and Edge; consent, data-retention and correction handling designed into the system. |

## 1.3. Project deliverables

| Category | Deliverables |
| --- | --- |
| Project-management deliverables | Project charter and scope statement; stakeholder list and organization; Development Case; Software Development Plan; WBS and WBS dictionary; iteration plans; effort, resource, cost and schedule baselines; risk, quality and communication plans; status and iteration assessments; change-request records; milestone reviews; pilot review; hand-over and lessons-learned records. |
| Requirements and design | Vision; Glossary; Stakeholder Requests; Business Rules; Domain Model; Use-Case Model and specifications; Software Requirements Specification (SRS); Supplementary Specification; Analysis Model; Software Architecture Document; user-interface prototype; test plan and test cases. |
| Product deliverables | Release 1.0 Core in operation at La Loy by 2 April 2027; Release 2.0 Growth in operation by 30 July 2027; productized Release 2.1 by 11 February 2028; test results; training for Manager and Front Staff; current-booking data migration; operating/support hand-over. |
| Closure deliverables | Pilot KPI results, expansion decision record, hand-over record, lessons learned, final status assessment and sponsor/customer sign-off. |

## 1.4. Exclusions

Split payments among multiple customers.

Customer-facing table photographs or distance-to-stage comparisons.

Restaurant-configurable booking rules beyond the rules agreed for the defined releases.

Payment-gateway fees, each restaurant's LINE Official Account plan and the pilot restaurant's own check-in tablet are not costs paid by the software house in this project budget.

Subscription revenue after the expansion decision and expansion operations beyond the project period are outside this project delivery budget.

## 1.5. Success criteria

| Success criterion | Target / evidence |
| --- | --- |
| Release milestones | Release 1.0 operating at La Loy by 2 Apr 2027; Release 2.0 by 30 Jul 2027; Release 2.1 by 11 Feb 2028; total project budget not above 1,010,590 THB. |
| Booking integrity | Zero double bookings on La Loy concert nights after go-live; table status maintained in real time on one record. |
| Customer experience | Booking completed within 3 minutes from table selection to confirmation without requiring a Manager reply. |
| Business outcome | No-show rate at La Loy reduced by 35% within six months of Release 2.0. |
| Operational quality | Check-in within 15 seconds per table; at least 5 transactions per second at booking-open; transaction response time no more than 2 seconds; recovery within 2 hours during opening hours. |
| Cost ceiling | Restaurant hosting, APIs and LINE plan at or below 1,000 THB/month. |
| Expansion gate | La Loy meets pilot criteria and continues on a paid plan; at least 10 restaurants are on the waiting list; Release 2.1 meets the per-shop hosting/support cost assumptions. |

# 2. Work Breakdown Structure (WBS) and Tasks

The WBS is presented in a detailed schedule format, following the required headings: WBS ID, task, responsible role, duration, predecessor(s), start, finish, and expected output/milestone measure. Iteration dates follow the SEATS report; task-level durations and dependencies are planning estimates. The phase rows (0, 1, 2, 3, 4, 5, 6, 7, 8) are shown as navy bands.

| WBS ID | Task | Responsible Role | Duration | Predecessor(s) | Start | Finish | Expected Output / Milestone Measure |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 0 | Project initiation and risk-driven planning | Project Manager + Team | 4d | Start | 3 Aug 2026 | 6 Aug 2026 | Project kickoff; initial scope and stakeholder access confirmed |
| 0.1 | Confirm project objectives, stakeholders, and initial risks | Project Manager + System Analyst | 2d | Start | 3 Aug 2026 | 4 Aug 2026 | Stakeholder list and initial risk list |
| 0.2 | Define high-level scope, assumptions, and constraints | Project Manager + System Analyst | 2d | 0.1 | 5 Aug 2026 | 6 Aug 2026 | Initial scope baseline |
| 1 | Inception — planning and LCO | Project Manager + Team | 23d | 0 | 3 Aug 2026 | 2 Sep 2026 | LCO milestone approved |
| 1.1 | Elicit business problem and high-level features (I1) | System Analyst + Requirements Specifier | 16d | 0.2 | 3 Aug 2026 | 24 Aug 2026 | Problem statement, stakeholders, high-level features |
| 1.2 | Prepare Vision, Business Case, Development Case and WBS (I2) | Project Manager + System Analyst | 7d | 1.1 | 25 Aug 2026 | 2 Sep 2026 | Plans and WBS ready; LCO on 2 Sep 2026 |
| 2 | Elaboration — requirements and architecture | System Analyst + Team | 37d | 1 | 3 Sep 2026 | 23 Oct 2026 | LCA milestone approved |
| 2.1 | Specify reservation and QR check-in use cases (E1) | System Analyst + Requirements Specifier | 10d | 1.2 | 3 Sep 2026 | 16 Sep 2026 | Use-case specifications, SRS and Supplementary Specification |
| 2.2 | Create analysis model, architecture, UI prototype and test plan (E2) | System Analyst + Designer + QA | 27d | 2.1 | 17 Sep 2026 | 23 Oct 2026 | Architecture and SRS baseline; LCA on 23 Oct 2026 |
| 3 | Release 1.0 Core — construction | Requirements Specifier/Designer + System Analyst + QA | 84d | 2 | 26 Oct 2026 | 26 Feb 2027 | Core build reaches IOC |
| 3.1 | Build concert setup, zones, packages, table map and 15-minute hold (C1) | Designer + System Analyst | 40d | 2.2 | 26 Oct 2026 | 18 Dec 2026 | Table selection and hold workflow |
| 3.2 | Implement payment gateway, callbacks and staff accounts (C1) | System Analyst + Designer | 40d | 2.2 | 26 Oct 2026 | 18 Dec 2026 | Payment and staff access functions |
| 3.3 | Implement QR e-ticket, check-in, live booking view, audit and backup (C2) | Designer + System Analyst + QA | 40d | 3.1, 3.2 | 4 Jan 2027 | 26 Feb 2027 | Core functions integrated; IOC on 26 Feb 2027 |
| 4 | Release 1.0 — transition and go-live | QA + Project Manager + Restaurant users | 25d | 3 | 1 Mar 2027 | 2 Apr 2027 | Release 1.0 in operation |
| 4.1 | Run acceptance/load tests, train staff and migrate current bookings (T1) | QA + Project Manager + Manager | 25d | 3.3 | 1 Mar 2027 | 2 Apr 2027 | Go-live at La Loy by 2 Apr 2027 |
| 5 | Release 2.0 Growth | Whole project team | 84d | 4 | 5 Apr 2027 | 30 Jul 2027 | Release 2.0 in operation |
| 5.1 | Implement reminders, grace extension, waitlist, transfers and reports (C3) | Designer + System Analyst + Requirements Specifier | 60d | 4.1 | 5 Apr 2027 | 25 Jun 2027 | Growth features integrated |
| 5.2 | Test, train users and deploy Release 2.0 (T2) | QA + Project Manager + Restaurant users | 25d | 5.1 | 28 Jun 2027 | 30 Jul 2027 | Release 2.0 live by 30 Jul 2027 |
| 6 | Pilot operation and KPI monitoring (P1) | Project Manager + QA + Restaurant Manager | 261d | 5.2 | 2 Aug 2027 | 28 Jul 2028 | Pilot KPIs recorded on concert nights |
| 6.1 | Measure booking time, double bookings, no-shows, check-in and operating cost | Project Manager + QA + Manager | During pilot | 5.2 | 2 Aug 2027 | 28 Jul 2028 | Evidence for expansion gate |
| 7 | Release 2.1 productization | System Analyst + Designer + QA | 120d | 5.2 | 2 Aug 2027 | 11 Feb 2028 | Multi-tenant subscription product ready |
| 7.1 | Implement multi-tenant model, plans/limits, billing and self-service onboarding (C4) | System Analyst + Designer + Requirements Specifier | 120d | 5.2 | 2 Aug 2027 | 14 Jan 2028 | Release 2.1 productization build |
| 7.2 | Test and deploy Release 2.1 (T3) | QA + Whole project team | 20d | 7.1 | 17 Jan 2028 | 11 Feb 2028 | Release 2.1 by 11 Feb 2028 |
| 8 | Project closure and expansion decision | Project Manager + Sponsor + Restaurant Owner | 5d | 6.1, 7.2 | 24 Jul 2028 | 28 Jul 2028 | Pilot review, hand-over, lessons learned and expansion decision |

## 2.1. WBS dictionary (summary)

Each work package must have exactly one accountable owner role, defined acceptance evidence and a reviewer who is not the author. The Project Manager maintains the WBS baseline and records approved changes through the Change Control Board. Construction includes implementation by the Requirements Specifier/Designer and independent verification by the QA role, as described in the SEATS report.

## 2.2. WBS dictionary (worked examples)

Two architecturally critical work packages are expanded as full WBS dictionary entries with measurable acceptance criteria and precedence. The entries are contributed by the Requirements Specifier (Chawanakorn Sanannam) and are mapped to the WBS identifiers of Section 2.

| Field | 3.1 Table selection, hold and inventory rules | 3.3 QR e-ticket and check-in |
| --- | --- | --- |
| Accountable owner | System Analyst / Designer | Designer |
| Inputs | Use-case specifications; table/zone/package data model. | Confirmed booking record; payment-gateway confirmation webhook. |
| Outputs | Table map, 15-minute hold logic and inventory rules. | Signed QR e-ticket and door-validation endpoint. |
| Acceptance criteria | An automated test of 50 concurrent requests for the same table yields exactly 1 successful hold and 49 conflict rejections without deadlock; the hold releases at 15 minutes ± 5 seconds. | A unique signed QR code is generated per confirmed booking; tampered references are rejected; the validation endpoint responds in < 2 seconds; duplicate scans raise a warning to Front Staff. |
| Predecessor | 2.2 (requirements and architecture baseline) | 3.1 (hold) and 3.2 (payment) |

# 3. Effort Estimation

The source report's top-down baseline is 2,632 person-hours: 2,092 hours in Year 0 for the build and 540 hours in Year 1 for productization. The task-level split below is an indicative bottom-up planning estimate created for this deliverable; the totals reconcile exactly to the source baseline (0% percent difference) and to the labor cost of 846,600 THB.

| WBS ID | Work package group | Estimated effort (hours) | Period |
| --- | --- | --- | --- |
| 0–1.2 | Initiation, planning and LCO | 128 | Year 0 |
| 2.1–2.2 | Requirements, analysis, architecture and prototype | 320 | Year 0 |
| 3.1–3.3 | Release 1.0 construction | 800 | Year 0 |
| 4.1 | Release 1.0 testing, training and go-live | 190 | Year 0 |
| 5.1 | Release 2.0 construction | 504 | Year 0 |
| 5.2 | Release 2.0 test and deployment | 150 | Year 0 |
| 6 + 7.1 | Pilot monitoring and Release 2.1 construction | 480 | Year 1 |
| 7.2 + 8 | Release 2.1 testing and close-out | 60 | Year 1 |
| TOTAL |  | 2,632 | Year 0: 2,092; Year 1: 540 |

## 3.1. Effort by role

| Role / team member | Hours | Rate (THB/hour) | Labor cost (THB) |
| --- | --- | --- | --- |
| Project Manager / Change Control Manager — Boonnisa Tangjitpermkwamdee | 434 | 350 | 151,900 |
| System Analyst / Software Architect — Sirapatr Chalermwattanatrai | 706 | 350 | 247,100 |
| Requirements Specifier / UI Designer / Designer — Chawanakorn Sanannam | 842 | 300 | 252,600 |
| Quality Assurance / Tester — Watayut Aiamanan | 650 | 300 | 195,000 |
| TOTAL | 2,632 | — | 846,600 |

The four engineers are part-time resources. The report assumes approximately 6–16 hours per week per engineer in Year 0 and 2–7.5 hours per week per engineer in Year 1, alongside other software-house work. This keeps every resource at or below 100% utilization; the Year-1 SaaS work (C4, T3) is deliberately back-loaded into the post-pilot window to remove the peak that would otherwise fall on the System Analyst and the Requirements Specifier.

# 4. Human and Physical Resource Assignment and Rates

Table below maps each human and physical resource to its assignment / responsibility and its rate or cost basis. Human rates are internal cost rates for 2026, expressed per hour and identical to the Milestone 1 rate baseline (350 THB/h for the PM/CM and SA roles; 300 THB/h for the RS/Designer and QA roles).

| Resource | Assignment / responsibility | Rate or cost basis |
| --- | --- | --- |
| Boonnisa Tangjitpermkwamdee | Project Manager and Change Control Manager; plans and controls scope, schedule, budget and risks; owns plans, iteration assessments, change control and closure. | 350 THB/hour; 434 hours; 151,900 THB |
| Sirapatr Chalermwattanatrai | System Analyst and Software Architect; leads elicitation, use-case model, architecture, integration assessment and technical design. | 350 THB/hour; 706 hours; 247,100 THB |
| Chawanakorn Sanannam | Requirements Specifier, User-Interface Designer and Designer; specifies requirements, prototypes the UI and contributes to implementation. | 300 THB/hour; 842 hours; 252,600 THB |
| Watayut Aiamanan | Quality Assurance / Tester; test planning, independent review, functional, regression, load and acceptance testing. | 300 THB/hour; 650 hours; 195,000 THB |
| Android phone and 10-inch tablet | Test devices for LINE in-app browser and check-in workflow; software-house project equipment. | One set; 15,000 THB |
| Cloud hosting, domain and development services | Development, staging and pilot hosting and domain. | Year 0 total 8,300 THB |
| Company/legal setup and pilot support | Registration/legal documents plus pilot hosting and support. | Year 1 total 52,200 THB (15,000 setup/legal; 37,200 hosting/support) |
| Pilot restaurant check-in tablet | Purchased by La Loy, not by the software house. | Excluded from project-house CAPEX; about 9,000 THB (restaurant) |

External dependencies include the LINE Platform / LIFF / Messaging API and the payment gateway. The restaurant maintains its own merchant account and LINE plan; gateway fees and the restaurant's LINE plan are not included as software-house costs.

# 5. Cost Estimate

The cost baseline below follows the SEATS report. Labor costs are consistent with the role hours and internal rates (Table 3.1). Following the PMBOK budget build-up, the activity/work-package estimates plus the contingency reserve form the cost baseline, and the cost baseline plus any management reserve forms the project budget.

| Cost item | Basis | Year 0 (THB) | Year 1 (THB) | Total (THB) |
| --- | --- | --- | --- | --- |
| Development labor | 2,092 h in Year 0; 540 h in Year 1 | 674,600 | 172,000 | 846,600 |
| Test devices (CAPEX) | Android phone and 10-inch tablet | 15,000 | 0 | 15,000 |
| Hosting and services / domain | Development, staging and pilot hosting | 8,300 | — | 8,300 |
| Company/legal setup, pilot hosting and support | Year 1 registration, legal, hosting and support | 0 | 52,200 | 52,200 |
| Contingency reserve | 10% reserve as stated in the source report | 69,790 | 18,700 | 88,490 |
| TOTAL PROJECT BUDGET |  | 767,690 | 242,900 | 1,010,590 |
| Less: La Loy pilot implementation fee | Revenue within the project | (150,000) | 0 | (150,000) |
| NET SOFTWARE-HOUSE INVESTMENT |  |  |  | 860,590 |

## 5.1. Cost-control rules

The Project Manager tracks actual effort against the 2,632-hour plan and the labor-cost baseline at each iteration assessment.

Any change affecting scope, budget or milestone dates must be assessed for impact and decided by the Change Control Board.

The contingency reserve is held for identified project risks; it is not treated as planned feature-development effort.

The budget excludes costs that the source report assigns to the restaurant, including its own LINE plan, merchant-account gateway fees and check-in tablet.

The source report describes the estimate as top-down and says a bottom-up WBS estimate should replace it at Milestone 2; the task-level breakdown in this document is therefore provisional until reviewed.

# 6. Schedule, Gantt Chart and Critical Path

The schedule follows the tailored Rational Unified Process (RUP) iterations in the SEATS report. The dates and milestone targets below are source-derived; the dependency chain and critical-path interpretation are planning analysis based on the listed work.

## 6.1. Iteration schedule

| Iteration / activity | Start | Finish | Main activity / milestone | Predecessor (planning) |
| --- | --- | --- | --- | --- |
| I1 — Inception | 3 Aug 2026 | 24 Aug 2026 | Scope, stakeholders, initial elicitation | — |
| I2 — Inception | 25 Aug 2026 | 2 Sep 2026 | Vision, plans, WBS; LCO | I1 |
| E1 — Elaboration | 3 Sep 2026 | 16 Sep 2026 | Use cases, SRS, supplementary requirements | I2 |
| E2 — Elaboration | 17 Sep 2026 | 23 Oct 2026 | Architecture, analysis, prototype, test plan; LCA | E1 |
| C1 — Construction | 26 Oct 2026 | 18 Dec 2026 | Concert setup, table map/hold, payment, staff accounts | E2 |
| C2 — Construction | 4 Jan 2027 | 26 Feb 2027 | QR, check-in, live view, audit, backup; IOC | C1 |
| T1 — Transition | 1 Mar 2027 | 2 Apr 2027 | Pilot, training, migration; Release 1.0 | C2 |
| C3 — Construction | 5 Apr 2027 | 25 Jun 2027 | Release 2.0 Growth features | T1 |
| T2 — Transition | 28 Jun 2027 | 30 Jul 2027 | Testing/training; Release 2.0 | C3 |
| P1 — Pilot | 2 Aug 2027 | 28 Jul 2028 | Pilot KPI measurement on concert nights | T2 |
| C4 — Construction | 2 Aug 2027 | 14 Jan 2028 | Multi-tenant productization, plans, billing | T2; runs during P1 |
| T3 — Transition | 17 Jan 2028 | 11 Feb 2028 | Release 2.1 testing/deployment | C4 |
| Close-out | 24 Jul 2028 | 28 Jul 2028 | Pilot review, expansion decision, hand-over | P1 and T3 |

## 6.2. Gantt chart view

Figure 1 presents the Gantt chart of the schedule baseline across the full 24-month project window (August 2026 – July 2028). The chart shows the iteration bars for each RUP phase together with the phase-gate milestones: LCO, LCA, IOC, the Release 1.0 and Release 2.0 go-lives, the Release 2.1 SaaS launch and project close-out.

Figure 1. Gantt chart of the SEATS schedule baseline (August 2026 – July 2028).

## 6.3. Critical path (dependency-based planning estimate)

The SEATS report does not publish a task-level critical path. Based on the planned release gates and logical dependencies, the provisional critical chain is:
I1 → I2 → E1 → E2 → C1 → C2 → T1 → C3 → T2 → P1 → Close-out. The C4 → T3 (Release 2.1) branch runs in parallel with P1 and carries planning float before close-out, so it does not drive the finish date. P1 pilot measurement runs in parallel with C4 and T3, but its longer duration controls the planned finish; close-out depends on both P1 and T3. Total path duration is 516 working days ≈ 24 calendar months. Any slippage on the critical chain directly extends the project finish date. The CPM values below are provisional planning estimates and should be validated against the resource-loaded calendar before baselining.

| ID | Activity / Milestone | Dur (wd) | Predecessor(s) | ES | EF | LS | LF | TS | Critical | Early start |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I1 | Inception — initial elicitation | 16 | Start | 0 | 16 | 0 | 16 | 0 | Yes | 03 Aug 2026 |
| I2 | Vision, plans and WBS / LCO | 7 | I1 | 16 | 23 | 16 | 23 | 0 | Yes | 25 Aug 2026 |
| E1 | Use cases and SRS requirements | 10 | I2 | 23 | 33 | 23 | 33 | 0 | Yes | 03 Sep 2026 |
| E2 | Architecture, analysis, prototype / LCA | 27 | E1 | 33 | 60 | 33 | 60 | 0 | Yes | 17 Sep 2026 |
| C1a | Table map and hold workflow | 40 | E2 | 60 | 100 | 60 | 100 | 0 | Yes | 26 Oct 2026 |
| C1b | Payment and staff access | 40 | E2 | 60 | 100 | 60 | 100 | 0 | Yes | 26 Oct 2026 |
| C2 | QR, check-in, live view, audit / IOC | 40 | C1a, C1b | 100 | 140 | 100 | 140 | 0 | Yes | 21 Dec 2026 |
| T1 | Release 1.0 transition and go-live | 25 | C2 | 140 | 165 | 140 | 165 | 0 | Yes | 15 Feb 2027 |
| C3 | Release 2.0 growth construction | 60 | T1 | 165 | 225 | 165 | 225 | 0 | Yes | 22 Mar 2027 |
| T2 | Release 2.0 testing and deployment | 25 | C3 | 225 | 250 | 225 | 250 | 0 | Yes | 14 Jun 2027 |
| P1 | Pilot operation and KPI monitoring | 261 | T2 | 250 | 511 | 250 | 511 | 0 | Yes | 19 Jul 2027 |
| C4 | Release 2.1 productization build | 120 | T2 | 250 | 370 | 371 | 491 | 121 | No | 19 Jul 2027 |
| T3 | Release 2.1 testing and deployment | 20 | C4 | 370 | 390 | 491 | 511 | 121 | No | 03 Jan 2028 |
| CL | Closure and expansion decision | 5 | P1, T3 | 511 | 516 | 511 | 516 | 0 | Yes | 18 Jul 2028 |

Table 6.3. CPM results — early/late start and finish, total slack (TS), and provisional criticality (working-day offsets). Activities with Total Slack = 0 are on the critical path.

## 6.4. Milestone control points

| Milestone | Target date | Acceptance / decision |
| --- | --- | --- |
| LCO | 2 Sep 2026 | Lifecycle objectives, scope direction and project viability reviewed. |
| LCA | 23 Oct 2026 | Architecture and SRS baseline approved; re-run financial analysis. |
| IOC | 26 Feb 2027 | Core build ready for transition and pilot readiness checks. |
| Release 1.0 live | 2 Apr 2027 | Core reservation and QR check-in operating at La Loy. |
| Release 2.0 live | 30 Jul 2027 | Growth features available; pilot year begins. |
| Release 2.1 | 11 Feb 2028 | Productized multi-tenant version ready. |
| Expansion decision / closure | 28 Jul 2028 | Review pilot KPIs, waiting-list threshold, operating costs, hand-over and sponsor/customer sign-off. |

# 7. Conclusion

The SEATS project is planned from 3 August 2026 to 28 July 2028, with three product releases and a pilot year. The source budget is 1,010,590 THB, including reserves, with 846,600 THB in labor cost for 2,632 hours. The WBS task split and the critical-path chain in this document are provisional planning estimates prepared to complete the requested project-management deliverables; they should be reviewed by the team and baselined at the Lifecycle Architecture milestone. The scope baseline (Sections 1–2), the effort and resource baselines (Sections 3–4), the cost baseline (Section 5) and the schedule baseline with the Gantt chart and critical path (Section 6) together form the Milestone 2 management baseline for the system, consistent with the SEATS Milestone 1 Part 2 Final Deliverables.