StudentID and Name:

StudentID and Name:

Exercise semester 1/2569

Exercise 3 Cost management (function point, cocomo II, earned value analysis) (45 points)

Submit your answer in a pdf file. Name the file by your name and student ID.

(23 points) Function point

1. (4 points) A web admin uses data analytic software to collect interaction data per event (or hit such as pageview, button click) when it happens.  Collected data in an event table include timestamp, user ID, session ID, page URL, event name etc. At the end of each week, the web admin displays a weekly report showing the activity level by day of the week, i.e. the number of hits, % of total hits, and the number of user sessions. Calculate the function point of this function of the software.

Display

Display

Activity Level by Day of the Week

Activity Level by Day of the Week

| Which function (EI, EO, EQ, ILF, or EIF)? |  |
| --- | --- |
| What is the number of DETs and what are they? |  |
| If counting FTRs is applicable to this function, what is the number of FTRs and what are they? If not, write N/A. |  |
| If counting RETs is applicable to this function, what is the number of RETs and what are they? If not, write N/A. |  |
| Rating (Low, Average, or High)? |  |
| Value? |  |

2. (4 points) The US Census Bureau hosts a web application that allows users to click on a location on the map (e.g. map location of Kansas City) to see some information about that location (i.e. city, state, population, and state coordinate). The US Census Bureau maintains its own state population data and obtains the state coordinate data from the Surveying and Mapping Section of the US Army [กรมแผนที่ทหาร]. Calculate the function point of this function of the application.

| Which function (EI, EO, EQ, ILF, or EIF)? |  |
| --- | --- |
| What is the number of DETs and what are they? |  |
| If counting FTRs is applicable to this function, what is the number of FTRs and what are they? If not, write N/A. |  |
| If counting RETs is applicable to this function, what is the number of RETs and what are they? If not, write N/A. |  |
| Rating (Low, Average, or High)? |  |
| Value? |  |

3. (4 points) The Mor Prom [หมอพร้อม] application of the Ministry of Public Health (MOPH) is the the government’s health application, first launched to provide the Covid vaccination service. Users provide personal data to register with this application, and the data are kept as part of the user data. Calculate the function point of this function of the application.

ที่อยู่

ที่อยู่

| Which function (EI, EO, EQ, ILF, or EIF)? |  |
| --- | --- |
| What is the number of DETs and what are they? |  |
| If counting FTRs is applicable to this function, what is the number of FTRs and what are they? If not, write N/A. |  |
| If counting RETs is applicable to this function, what is the number of RETs and what are they? If not, write N/A. |  |
| Rating (Low, Average, or High)? |  |
| Value? |  |

4. (4 points) The Mor Prom [หมอพร้อม] application stores the user data which consist of  the user’s personal data, i.e. 15 data fields, and the information about vaccine shots that the user has received, i.e. date of vaccination, vaccine name, vaccine manufacturer, vaccine lot, and vaccination site. Calculate the function point of this function of the application.

| Which function (EI, EO, EQ, ILF, or EIF)? |  |
| --- | --- |
| What is the number of DETs and what are they? |  |
| If counting FTRs is applicable to this function, what is the number of FTRs and what are they? If not, write N/A. |  |
| If counting RETs is applicable to this function, what is the number of RETs and what are they? If not, write N/A. |  |
| Rating (Low, Average, or High)? |  |
| Value? |  |

5. (4 points) The Mor Prom [หมอพร้อม] application connects to the Organ Donation API of the Thai Red Cross to access users’ organ donation data. The organ donation data are maintained by the Thai Red Cross system and are only referenced by the Mor Prom application. The organ donation data consist of donor information and information about the donated organs. The donor information includes national ID, title, first name, last name, date of birth, occupation, address, tumbol, district, province, postcode, house phone, and mobile phone. For each donated organ, the information includes the donation date, donated organ, and witness name. Calculate the function point of this function of the application.

| Which function (EI, EO, EQ, ILF, or EIF)? |  |
| --- | --- |
| What is the number of DETs and what are they? |  |
| If counting FTRs is applicable to this function, what is the number of FTRs and what are they? If not, write N/A. |  |
| If counting RETs is applicable to this function, what is the number of RETs and what are they? If not, write N/A. |  |
| Rating (Low, Average, or High)? |  |
| Value? |  |

6. (3 points) Suppose an application has the following number of functions of various sizes.

|  | No. of low | No. of average | No. of high |
| --- | --- | --- | --- |
| External Input (EI) | 3 | 1 | 0 |
| External Output (EO) | 1 | 0 | 0 |
| External Inquiry (EQ) | 2 | 1 | 0 |
| Internal Logical File (ILF) | 5 | 0 | 0 |
| External Interface File (EIF) | 1 | 0 | 0 |

Calculate the unadjusted function points of this application.

|  | Low | Average | High | Total |
| --- | --- | --- | --- | --- |
| External Input (EI) | ……*3 = …... | ……*4 = …….. | ………*6 = ……….. |  |
| External Output (EO) | ……*4 = …….. | …..…*5 = …….. | ………*7 = ………… |  |
| External Inquiry (EQ) | ……*3 = …….. | ….…*4 = ….….. | …..…*6 = …..…….. |  |
| Internal Logical File (ILF) | ……*7 = ……. | ………*10 = ……….. | ………*15 = ……….. |  |
| External Interface File (EIF) | ……*5 = …….. | ………*7 = ……….. | ………*10 = ……….. |  |
| Unadjusted FP |  |  |  |  |

(8 points) COCOMO II Post-architecture Model

1. Suppose the application size is 67 function points. If the application is written in Javascript and the average gearing factor is ……., the application size is ………………………………………….. KLOC. (See gearing factor here https://www.qsm.com/resources/function-point-languages-table)

2. Scale Factor (SF) (Rate SF as you see fit.)

| Scale Factor (SF) | Rating | Score |
| --- | --- | --- |
| Precedentedness (PREC) |  |  |
| Development Flexibility (FLEX) |  |  |
| Architecture / Risk Resolution (RESL) |  |  |
| Team Cohesion (TEAM) |  |  |
| Process Maturity (PMAT) |  |  |
| SF |  |  |

3. Effort Multipliers (EM) (Rate EM as you see fit.)

| Effort Multiplier (EM) | Rating | Score |
| --- | --- | --- |
| Product factors |  |  |
| Required Software Reliability (RELY) |  |  |
| Data Base Size (DATA) |  |  |
| Product Complexity (CPLX) |  |  |
| Developed for Reusability (RUSE) |  |  |
| Documentation Match to Life-Cycle Needs (DOCU) |  |  |
| Platform factors |  |  |
| Execution Time Constraint (TIME) |  |  |
| Main Storage Constraint (STOR) |  |  |
| Platform Volatility (PVOL) |  |  |
| Personnel factors |  |  |
| Analyst Capability (ACAP) |  |  |
| Programmer Capability (PCAP) |  |  |
| Personnel Continuity (PCON) |  |  |
| Applications Experience (APEX) |  |  |
| Platform Experience (PLEX) |  |  |
| Language and Tool Experience (LTEX) |  |  |
| Project factors |  |  |
| Use of Software Tools (TOOL) |  |  |
| Multisite Development (SITE) |  |  |
| Required Development Schedule (SCED) |  |  |
| EM |  |  |

Show how you calculate for the following. (แทนค่าในสมการให้ดูด้วย)

4. E = ………………………………….………………………………………..…………….……………………………………..

5. Project effort PM = ……………………………………………………………………………. person-months

6. Nominal effort PMNS = ………………………………………………………………………. person-months

7. Calendar time to develop TDEV is ……………………………………………………………….. months

8. Staff size required to do the amount of work in 5. during the calendar time in 7. is …………………………………………………………………………………………………………………………. persons

(6 points) Cost estimation

Show your calculations for the following.

Suppose the estimated effort for the project is 5 person-months. The project has a fixed number of staff that will be working on the project and agile methodology (Scrum) is used. The distribution of the project effort on different project activities and on different sprint activities is shown in the table below.

| Project Activity | % of Project Effort PM |  |  |
| --- | --- | --- | --- |
| Management | 10% |  |  |
| Analysis | 10% |  |  |
| Sprint 1 | 20% | Sprint Activity | % of Sprint Effort |
|  |  | Analysis | 5 |
|  |  | Design | 15 |
|  |  | Implementation | 50 |
|  |  | Testing | 20 |
|  |  | Management | 10 |
| Sprint 2 | 20% | Sprint Activity | % of Sprint Effort |
|  |  | Analysis | 5 |
|  |  | Design | 15 |
|  |  | Implementation | 50 |
|  |  | Testing | 20 |
|  |  | Management | 10 |
| Sprint 3 | 20% | Sprint Activity | % of Sprint Effort |
|  |  | Analysis | 5 |
|  |  | Design | 15 |
|  |  | Implementation | 50 |
|  |  | Testing | 20 |
|  |  | Management | 10 |
| Sprint 4 | 20% | Sprint Activity | % of Sprint Effort |
|  |  | Analysis | 5 |
|  |  | Design | 15 |
|  |  | Implementation | 50 |
|  |  | Testing | 20 |
|  |  | Management | 10 |

In the table below, show how to calculate % of project effort of each project activity, activity effort in person-months, activity labor cost, and total project labor cost. (แสดงการคำนวณให้ดูด้วย)

| Project Activity | % of Project Effort PM | Activity Effort (Person-Months) | Average Activity Labor Cost Per Person-Month (THB) | Activity Labor Cost (THB) |
| --- | --- | --- | --- | --- |
| Management |  |  | 90,000 |  |
| Analysis |  |  | 50,000 |  |
| Design |  |  | 50,000 |  |
| Implementation |  |  | 30,000 |  |
| Testing |  |  | 30,000 |  |
| Total Project Labor Cost |  |  |  |  |

(8 points) Earned Value Analysis

Assume we are through the second month of a one-year project that has a total budget of 1,200,000 bahts. The amount budgeted for the first two months is 230,000 bahts, but the work that has been finished in these two months is worth 200,000 bahts of the budget. The actual cost for the first two months is 250,000 bahts. (แสดงการคำนวณให้ดูด้วย)

Budget at completion (BAC) = …………………………………..………………………………………………………

Planned Value (PV) = …………………………………………………………………………………………………………

Earned Value (EV) = ……………………………………………………………………………………………………………

Actual Cost (AC) = ………………………………………………………………………………………………………………

Cost Variance (CV) = …………………………………………………………………………..………………………………

Schedule Variance (SV) = ……………………………………………………………………………..……………………

Cost Performance Index (CPI) = ……………………………………………………………………..…………………

Schedule Performance Index (SPI) = ……………………………………………………………………..…………

Estimate at completion (EAC) = …………………………………………………………………………….…………

Estimated time to complete = ………………………………….……………………………………………………..

Estimated to complete (ETC) = …………………………………………………………………………….………….

To complete the project with the original budget, To-complete performance index (TCPI) = ……………………………………………………………………………………………….……………………………..

1. Considering the Cost Performance Index (CPI) and Schedule Performance Index (SPI), how is the project doing?

under budget		 on budget 		 over budget

ahead of schedule		 on schedule 	 behind schedule

2. If the team continues to perform at the current cost efficiency, the cost of completing the project would be …………………………..…………………………………………………………

3. If the team continues to perform at the current schedule efficiency, the time of completing the project would be ………………………………………………………………………….…………

4. Considering the To-complete performance index (TCPI), is the original budget reasonable for completing the project? Why? ……………….……………………………………………….

……………………………………………………………………………………………………………………………………………..

……………………………………………………………………………………………………………………………………………..